## Source Index
Source | Type | URL / Path | Read Status | PC Usage | Notes
[Terry]pumpkin-virtual-project-brief.md | Google Doc | https://docs.google.com/document/d/1gagPgWPtILfaHzHTf9aCvDohKfEJs20gMEI9x7ihhzM | Reviewed | Studio operating model | Defines Pumpkin Virtual, 28 agents, $15 goal.
Gorilla Gun: Survivor資料表 | Google Sheet | https://docs.google.com/spreadsheets/d/1v0El62touwTJxqC0jtxu0k32rGUWsxOPRIO-SWIdtno | Reviewed | VR content source | 18 tabs reviewed at summary/detail level.
Meta listing | Store page | https://www.meta.com/zh-tw/experiences/gorilla-gun-survivor/25330246106588143/ | Public listing checked via web index | Positioning / marketing | Live VR title; public index shows Quest support, early access, rating snapshot.
Quest Store DB listing | Public index | https://queststoredb.com/game/gorilla-gun-survivor-25330246106588143/ | Reviewed | Store metadata | Used because Meta page itself is hard to fetch directly in tool.
Marketing schedule | Google Sheet | https://docs.google.com/spreadsheets/d/1VrLgiXE1wJfBa7fkKTV2SFYw8ho0v70-lqk4yM_ePqw | Partially reviewed | Steam / Meta checklist | Useful for PC store preparation.
GG_PC_0511.mp4 | Local video | C:\Users\pumpkin018\Desktop\GG_PC_0511.mp4 | Located, not visually decoded | Current PC progress reference | ffmpeg/ffprobe unavailable in this runtime. Needs video review pass.
NotebookLM 2026 meeting record | NotebookLM | https://notebooklm.google.com/notebook/15565388-0cdc-4bb8-815e-f3d1b08e4972 | Blocked | Final desired content | Needs export to Doc/PDF or authenticated browser access.
NotebookLM art design | NotebookLM | https://notebooklm.google.com/notebook/ed2f41b2-6716-488d-b88a-3b05be37afad | Blocked | Art bible source | Needs export or browser access.
NotebookLM 2026 alt | NotebookLM | https://notebooklm.google.com/notebook/4e6afe6e-96a1-4500-8367-df2e86a3f765 | Blocked | Meeting records | Needs export or browser access.
NotebookLM 2025 | NotebookLM | https://notebooklm.google.com/notebook/27aa6d19-98af-4101-b71b-77dfdb620dd4 | Blocked | Historical decisions | Needs export or browser access.
Public PC GitHub clone | Repo | F:\claude\Terry.Agent\gorilla-gun-survivor | Reviewed | Code baseline | May not match latest private PC build/video.

## VR Sheet Map
VR Tab | PC Relevance | Reuse Strategy | Owner | Notes
資料連結 | High | Copy links into PC source index | CEO | Contains Figma and marketing sheet hyperlinks.
遊戲兵推數值計算 | High | Reference for difficulty/boss/weapon curve | Balance Architect | Needs PC retune, not direct copy.
狀態與效果 | High | Convert to PC status/effect schema | Balance + Gameplay | Base and evolved effects are core content.
通用強化表 | Medium | Convert later into PC meta progression | Systems | Good permanent upgrade source.
關卡模塊設計 | Low now | Use as theme list only | Cartograph | Currently sparse.
地下墓穴無限死鬥 關卡事件表 | High | Use as 15-min event spine | Systems + QA | Strong source for spawn/event pacing.
角色表 | Medium | Defer until PC core loop stable | Narrative + Systems | Multiple characters/ultimates too large for v0.1.
角色基本數值 | Medium | Use definitions and XP curve reference | Balance | PC may need shorter curve.
卡牌 | High | Convert cards/relics in waves | Balance | Large relic content library.
武器總表 | High | Convert first 10 PC weapons | Combat + Gameplay | At least 20 weapons visible.
地圖 | Medium | Convert into PC arena rules | Cartograph | Spawn points, facilities, traps are useful.
大廳 | Medium | Use as meta hub spec | Systems + UI | NPC unlocks and playful secrets.
卡片與事件機率 | High | Use as card generation rules | Balance | Pity rules and chest monster probabilities.
Sound | High | Convert to PC sound backlog | Audio | Marks completed/imported/missing assets.
傷害計算 | High | Use for damage pipeline order | Gameplay | Tracking -> damage -> effect -> bounce -> pierce.
UI概念 | Medium | Use rarity colors and HUD rules | UI/UX | Needs PC HUD redesign.
移動 | High | Translate to PC movement values | Combat | Grapple, dash, double jump, glide.
核心刷寶系統 | Unknown | Revisit | Systems | Read returned empty in sampled range.

## PC Migration Matrix
System | VR Source | Current PC State | PC Decision | Priority | Owner
Movement | 移動 | User reports sprint/double jump/dash/grapple in newer PC build | Formalize PC values and cooldowns | P0 | Combat Designer
Lobby | 大廳 | User reports lobby/interactables/settings | Keep as hub, do not overbuild before combat loop | P1 | Systems + UI
Weapons | 武器總表 | Public prototype has 7 auto weapons | Import in waves: current 7 + 3 VR weapons first | P0 | Combat + Gameplay
Cards/relics | 卡牌 | Public prototype has 18 cards | Build PC card schema and import first 12 relics | P0 | Balance
Elements | 狀態與效果 | Simplified 4 x 3 tiers in prototype | Keep base elements, add evolved effects after VFX/perf pass | P1 | Balance + VFX
Enemies | 地下墓穴事件 + current EnemyTypes | Public prototype has 10 enemy types | Map VR enemy roster and boss cadence to PC | P0 | Gameplay
Boss timing | 地下墓穴無限死鬥 | Miniboss appears at 120s in public prototype | Use 5-min vertical slice then 15-min full loop | P1 | Systems
Sound | Sound | Prototype uses WebAudio synthetic SFX | Import real audio backlog where available | P2 | Audio
QA automation | N/A | Not present | Create browser run report and metrics capture | P0 | QA + Tools
Marketing | Marketing sheet + Meta listing | Not in repo | Prepare Steam PC checklist after gameplay lock | P2 | CMO

## Sprint 0 Tasks
Task ID | Task | Owner | Output | Status
S0-001 | Export or grant readable access to NotebookLM 2026 meeting record | Human owner | Google Doc/PDF or browser-readable source | Blocked
S0-002 | Confirm latest PC repo/build path matching GG_PC_0511.mp4 | CTO | Repo/path note | Open
S0-003 | Run local PC build and record baseline console/FPS | QA | qa/reports/baseline.md | Open
S0-004 | Define PC v0.1 movement values | Combat Designer | design/pc-controls.md | Open
S0-005 | Create weapon migration table | Balance + Gameplay | design/pc-data/weapons.md | Open
S0-006 | Create card/effect migration table | Balance | design/pc-data/cards-effects.md | Open
S0-007 | Create browser QA automation spec | Tools + QA | automation/workflows/browser-qa.md | Open
S0-008 | Prepare PC Steam store checklist from marketing sheet | CMO | marketing/store/steam-checklist.md | Open

## Blockers
Blocker | Impact | Resolution Needed | Owner
NotebookLM cannot be read through Drive connector | Missing final 2026 meeting decisions | Export notebooks to Google Doc/PDF or allow authenticated browser session | Human owner
Video cannot be decoded in current runtime | Cannot visually verify latest PC progress | Install/allow ffmpeg or review through browser/video tooling | Tools Programmer
Public GitHub may not match latest PC build | Risk of building on old baseline | Confirm latest source path/repo | CTO
Original source docs are read-only by instruction | Need separate PC working files | Continue using new local docs and new PC sheet only | CEO

## Team Terminals
Terminal | Role | Allowed Write Scope | Primary Prompt
T-CEO | Pumpkin King / CEO | studio/briefs, studio/decisions, studio/prompts | studio/prompts/ceo-pumpkin-king.md
T-CTO | Circuit / CTO | src review, architecture docs | TBD
T-D2 | Balance Architect | design/pc-data | TBD
T-D3 | Combat Designer | design/pc-controls.md | TBD
T-P2 | Gameplay Programmer | src/weapon, src/enemy, src/progression by assignment | TBD
T-QA | QA Analyst | qa/reports, qa/bugs | TBD
T-TOOLS | Tools Programmer | automation, tools | TBD
T-CMO | Harvest / CMO | marketing | TBD
T-CAO | Raven / CAO | art, studio/bibles | TBD